## Template Project Plan
Status | Milestone | Primary Responsibility | IRM Contact | Primary Customer Contact | Progress | Due Date | Comments
| Learn Phase | [5 empty] | The overall purpose of this phase is to provide customer orientation materials & allow time for questions to be answered
| Distribute Migration Help Materials | Iron Mountain | Kathleen Andrews
| Review Migration Help Material | Customer |  |  |  |  | Primary customer contact to review materials
| Schedule Migration Review call, optional | Customer |  |  |  |  | Reach out to IRM Contact for questions. Additional Q&A sessions can be scheduled per your needs. Schedule Call
| Prepare Phase: Project Management | [5 empty] | The overall purpose of this phase is to plan out the joint project management approach between Iron Mountain and the customer.
| Identify Customer Migration Leader Contact | Customer |  |  |  |  | Notify the Primary Iron Mountain contact as to the Customer Migration Leader for coordination purposes.
| Amend Template Project Plan | Customer |  | Customer Migration Leader |  |  | Review this project template and customize for the specific customer situation
| Amend Template Communications Plan | Customer |  | Customer Migration Leader |  |  | Review the template communications plan and proposed communications. Identify who should send out the communications
| Confirm Target Migration Date | Customer |  | Customer Migration Leader |  |  | Based on the amended project plan & migration date, confirm target implementation date
| Prepare Phase: Technical Readiness | [5 empty] | The overall purpose of this phase is to have the customer make any needed mandatory changes for the Policy Center migration.
Provision Environment
| Create New Policy Center Tenant | Iron Mountain
Notification
| Reminder notice sent to Customer Migration Leader | Iron Mountain | Kathleen Andrews |  |  | 10 days in advance of migration date
| Users notified about the upcoming migration. | Customer |  | Customer Migration Leader |  | 10 - 12 days in advance of migration date
Access
| Single Sign On (SSO) | Joint Responsibility
| Identify Single Sign On Focal Point | Customer |  | Customer Migration Leader |  |  | The customer identifies the correct focal point in their organization for single sign on integration
| Provide Single Sign On Materials to SSO Focal Point | Customer |  | Customer Migration Leader |  | at least 3 weeks in advance of migration date
| Complete SSO Form | Customer |  | Single Sign On Focal
| Implement Single Sign On | Joint Responsibility | PCS Support | Single Sign On Focal
| Test Single Sign On | Joint Responsibility | PCS Support | Single Sign On Focal
| Run SSO User preload script to migrate users to new platform. | Iron Mountain | PCS Support |  |  | 1 day in advance of migration date
Update URLS
| Update documents with embedded URL Links | Customer |  |  |  |  | Identify and update any documents that may have old Policy Center hyperlinks. These will be posted later on migration day
| Update any internal intranet sites with embedded URL links | Customer |  |  |  |  | Depending on the Web Site update practices within the customer, this may require it's own project plan. This task represents the set of work required to identify affected web pages, make the changes in any required test environments. The production intranet site should not be updated until Migration day.
| Migrate Phase | [5 empty] | The overall purpose is to execute the migration activities
| Go / No Go Decision | Joint Responsibility | Kathleen Andrews | Customer Migration Focal |  | 3 days before migration
| Place Legacy Platform in read only mode | Iron Mountain | Tech Migration Leader |  |  | as migration begins | This prevents updates to the legacy platform while the migration is occurring.
| Execute automated migration | Iron Mountain | Tech Migration Leader |  |  |  | This automatically copies all customer information from the old Policy Center to the new Policy Center
| Conduct quality assurance on new platform | Iron Mountain | Tech Migration Leader | Optional QA: Customer Migration Leader |  |  | Customer Migration Focal will determine if they wish to perform a separate quality assurance validation.
| Notify Customer migration is complete | Iron Mountain | Tech Migration Leader | Customer Migration Focal
| Post Updated URL Materials | Customer |  | Customer Migration Focal
| Post Documents Updated in Prepare Phase | Customer |  | Customer Migration Focal |  |  | These documents were previously updated during the Prepare Phase
| Update Production Intranet site with new URLs | Customer |  | Customer Migration Focal |  |  | these intranet sites were previously identified and updates made / tested per customers internal policies on how intranet changes are made. This is just the production migration step.
Archive Phase